## Sheet1
ID | Story | Time Estimation (Hours) | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | Status
TASK 1 | User can import excel file which includes checklist | 19 | 9 |  |  |  | In progress
TASK 2 | User can display file browsing function | 6 | 6
TASK 3 | User can display details of each checklist item | 10 | 0 |  |  |  | Not started
TASK 4 | Setting up environment | 6 | 6 |  |  |  | Completed
TASK 5 | User can modify status of test case | 4 | 0 |  |  |  | Not Started
TASK 6 | User can modify if test case is automated or not. | 16 | 0 |  |  |  | Not Started
TASK 7 | User can display results of test case | 4 | 0 |  |  |  | Not started
TASK 8 | User can export results of test case | 7 | 0 |  |  |  | Not started
Estimated | Ideal Time | 72 | 54 | 36 | 18 | 0
ACTUAL | Actual Time | 72 | 51
| Ideal Time | 72 | 54 | 36 | 18 | 0